## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a user, I want to submit a question, AI response and reference answer for evaluation. | Must have | Evaluation pipeline | Project Team | Completed
Sprint 1 | Sprint 1 | US-02 | As a user, I want a reference knowledge base with semantic retrieval to ground evaluation in evidence. | Must have | Database + embeddings | Project Team | Completed
Sprint 2 | Sprint 2 | US-03 | As a user, I want separate relevance, accuracy and hallucination assessments for an AI response. | Must have | US-01; US-02 | Project Team | Completed
Sprint 2 | Sprint 2 | US-04 | As a user, I want completeness scoring and a final weighted PASS/REVIEW/FAIL verdict. | Must have | Agent outputs | Project Team | Completed
Sprint 3 | Sprint 3 | US-05 | As a user, I want to review past evaluations and dashboard statistics. | Must have | Evaluation persistence | Project Team | Completed
Sprint 3 | Sprint 3 | US-06 | As a user, I want to inspect detailed multi-agent evaluation results and reasoning. | Must have | Evaluation detail API + UI | Project Team | Implemented; production API verified
Sprint 4 | Sprint 4 | US-07 | As a user, I want to upload a CSV and evaluate multiple responses in one batch. | Must have | CSV parser + evaluation pipeline | Project Team | Completed; batch endpoint verified
Sprint 4 | Sprint 4 | US-08 | As a user, I want to download a PDF for a single evaluation. | Must have | Evaluation record + PDF service | Project Team | Completed; endpoint verified
Sprint 4 | Sprint 4 | US-09 | As a user, I want to download a PDF summary for a batch evaluation. | Must have | Batch processing + PDF service | Project Team | Completed; endpoint verified
Sprint 4 | Sprint 4 | US-10 | As a project reviewer, I want regression, benchmark and unseen-validation results documented. | Must have | Test suite + benchmark data | Project Team | Completed; 57/57 tests reported
Sprint 4 | Sprint 4 | US-11 | As a project reviewer, I want the application deployed with a production frontend, API and cloud database. | Must have | Vercel + Neon PostgreSQL/pgvector | Project Team | Deployed; production checks reported
Sprint 4 / M4.4 | Sprint 4 / M4.4 | US-12 | As a project reviewer, I want technical documentation, architecture diagrams, project report and demo material. | Must have | Verified code audit and test evidence | Project Team | Documentation deliverables being finalized
Note: Dates, individual names, and daily effort allocations were not provided; these were left blank rather than fabricated.
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG
US-10 | M4-01 | Review full regression test suite |  |  | Project Team | Testing | Completed | 6
US-10 | M4-02 | Run 50-question benchmark and record verdict agreement / hallucination metrics |  |  | Project Team | Testing | Completed | 6
US-10 | M4-03 | Run unseen 25-case validation and document mismatches |  |  | Project Team | Testing | Completed | 4
US-05 | M4-04 | Verify dashboard statistics endpoint and history aggregation |  |  | Project Team | Integration Testing | Completed | 3
US-06 | M4-05 | Trace Inspect flow from frontend click through API and database response |  |  | Project Team | Integration Testing | Production API verified; UI E2E evidence should be retained | 5
US-07 | M4-06 | Verify batch CSV processing and batch history |  |  | Project Team | Integration Testing | Completed; exact CSV aliases require source-code confirmation | 5
US-08 | M4-07 | Verify single evaluation PDF export |  |  | Project Team | Testing | Completed | 2
US-09 | M4-08 | Verify batch PDF export |  |  | Project Team | Testing | Completed | 3
US-11 | M4-09 | Resolve Vercel SPA output path and routing |  |  | Project Team | Deployment | Completed | 4
US-11 | M4-10 | Resolve serverless database/cache compatibility |  |  | Project Team | Deployment | Completed | 5
US-11 | M4-11 | Configure production PostgreSQL/pgvector and verify API health |  |  | Project Team | Deployment | Production checks reported successful | 5
US-12 | M4-12 | Audit implementation details for documentation: schemas, routes, formulas, CSV contract |  |  | Project Team | Documentation | In progress / confirm from current source code | 6
US-12 | M4-13 | Prepare final technical report, architecture diagrams and presentation |  |  | Project Team | Documentation | In progress | 8
US-12 | M4-14 | Prepare final end-to-end demonstration script |  |  | Project Team | Documentation | In progress | 3
Note: Dates, individual names, and daily effort allocations were not provided; these were left blank rather than fabricated.
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
M4 | Final verification | Docker CLI was unavailable on the original Windows host; production validation was performed through Vercel endpoints. | Validated production routes and APIs; retained explicit note that browser-level UI E2E should be separately evidenced.
Note: Dates, individual names, and daily effort allocations were not provided; these were left blank rather than fabricated.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 |  |  |  |  | Continue using regression tests and production endpoint checks as release gates. | Avoid declaring complete UI functionality from API checks alone. | Keep code, tests, and documentation aligned; verify exact CSV headers and dashboard rounding from implementation. | M4 documentation audit includes explicit confirmed/not-confirmed status.
2
3
4
5
6
7
Note: Dates, individual names, and daily effort allocations were not provided; these were left blank rather than fabricated.