## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
DEF-001 | Project Team |  | Batch CSV header contract was unclear between sample headers (question,response,reference) and documented headers (question,ai_response,reference_answer). | M4 | Backend | Validation/Documentation | Audit parser and align official CSV example with accepted headers; aliases must only be documented if implemented. |  | Closed | Documentation ambiguity identified; final accepted aliases must be verified against current parser code.
DEF-002 | Project Team |  | Production root URL served compiled JavaScript instead of the React SPA because server bundle and frontend output shared dist output. | M4 | Frontend | Configuration | Changed Vite output to dist/index.html and separated server build output from frontend build. |  | Closed | Commit reported: 9a22d0e; production root verified as HTML.
DEF-003 | Project Team |  | Vercel serverless runtime could fall back to SQLite in a read-only code directory when PostgreSQL connection configuration failed. | M4 | Backend | Logical/Configuration | Adjusted serverless SQLite fallback location to writable /tmp and corrected database connection handling. |  | Closed | Commit reported: 6d7a5ba; production health endpoint later reported DB connected.
DEF-004 | Project Team |  | Frontend API base URL could produce duplicated /api path segments in some requests. | M4 | Frontend | Logical | Normalized API base URL handling in the frontend API service. |  | Closed | Commit reported: 8ce4a3c; verify relevant routes in current production if changes recur.
DEF-005 | Project Team |  | Production backend required serverless-compatible FastEmbed cache location to avoid writing model files to read-only filesystem. | M4 | Backend | Configuration | Redirected FastEmbed/Hugging Face cache to /tmp in serverless environments. |  | Closed | Commit reported: 560302f; deployment endpoint checks were reported successful.
DEF-006 | Project Team |  | Required Python dependencies for embedding and PostgreSQL driver were missing from backend requirements. | M4 | Backend | Configuration | Added fastembed and psycopg2-binary dependencies to backend requirements. |  | Closed | Commit reported: 2409191; regression suite reported 57/57 passing.
DEF-007 | Project Team |  | Initial Alembic migration was stale compared with the current ORM schema. | M4 | Backend/Database | Logical | Updated initial migration and Alembic environment to align with the current six-table ORM schema and synchronous engine. |  | Closed | Commit reported: 2409191; migration was reported applied to Neon.
DEF-008 | Project Team |  | Production client documentation/modal examples used hardcoded localhost API URLs. | M4 | Frontend | Configuration | Replaced hardcoded localhost references with centralized API_BASE_URL handling. |  | Closed | Commit reported: 2409191; TypeScript check and build reported successful.
DEF-009 | Project Team |  | Frontend production bundle was larger than desired and page imports were not split. | M4 | Frontend | Performance | Added React.lazy and Suspense route-level code splitting. |  | Closed | Commit reported: 2409191; reported main bundle reduced from 746 kB to 333 kB.
DEF-010 | Project Team |  | Evaluation Inspect detail flow required production verification that all five agent result sections were returned for a selected evaluation. | M4 | Full Stack | Logical | Verified GET /api/evaluate/{evaluation_id} and confirmed relevance, accuracy, hallucination, completeness and verdict detail in the response. |  | Closed | Production API verification was reported successful; browser-level Inspect UI E2E should be separately evidenced.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others